## Sheet1
TASK |  |  |  |  | (Develop) Due date |  | State |  |  |  | 비고
구분 | 1Depth | 2Depth | 화면코드 | 퍼블 | Start | End | 개발 이슈사항 공유 | (개발자)단위 테스트 | (기획자)단위 테스트 | (사용자)단위 테스트
회원가입 | 회원가입 |  | U0001 | 미완료 | 2022-07-05 | 2022-07-06 |  | X | X | X
| 회원가입완료 |  | U0002 | 미완료 | 2022-07-05 | 2022-07-06 |  | X | X | X
| 아이디 찾기 |  | U0003 | 미완료 |  |  |  | X | X | X
| 패스워드 찾기 |  | U0004 | 미완료 |  |  |  | X | X | X
로그인 | 로그인 |  | U0005 | 미완료 |  |  |  | X | X | X
| 미인증시 인증번호 재전송 |  | U0006 | 미완료 |  |  |  | X | X | X
| 미인증 재전송 완료 |  | U0007 | 미완료 |  |  |  | X | X | X
메인 | 메인 |  | M1000 | 미완료 |  |  |  | X | X | X
| 메인 – 확장_국가 |  | M1001 | 미완료 |  |  |  | X | X | X
| 메인 – 확장_국가_서브카테고리 |  | M1002 | 미완료 |  |  |  | X | X | X
판매 | SELL |  | S1000 | 미완료 |  |  |  | X | X | X
| SELL_Detail_일반코인 |  | S1001 | 미완료 |  |  |  | X | X | X
| SELL_Detail_제휴사코인 |  | S1002 | 미완료 |  |  |  | X | X | X
구매 | BUY |  | B1000 | 미완료 |  |  |  | X | X | X
| BUY_Detail_제휴사코인 |  | B1001 | 미완료 |  |  |  | X | X | X
| BUY_Detail_일반코인 |  | B1002 | 미완료 |  |  |  | X | X | X
| 비트피어 제휴 |  | BP200 | 미완료 |  |  |  | X | X | X
Mypage | Mypage_Buys history |  | MP010 | 미완료 |  |  |  | X | X | X
| Mypage_Sells history |  | MP020 | 미완료 |  |  |  | X | X | X
| Affiliate Wallet |  | MP030 | 미완료 |  |  |  | X | X | X
|  | Coin Send | MP031 | 미완료 |  |  |  | X | X | X
|  | Coin Receive | MP032 | 미완료 |  |  |  | X | X | X
| Affiliate Coin Sell registration |  | MP040 | 미완료 |  |  |  | X | X | X
| Affiliate Coin Sell registration(제휴사) |  | MP041 | 미완료 |  |  |  | X | X | X
| Affiliate Coin Buy registration |  | MP050 | 미완료 |  |  |  | X | X | X
| Affiliate Coin Buy registration(제휴사) |  | MP051 | 미완료 |  |  |  | X | X | X
| My Information |  | MP060 | 미완료 |  |  |  | X | X | X
| Seller Certification |  | MP070 | 미완료 |  |  |  | X | X | X
| Affiliate code registration |  | MP080 | 미완료 |  |  |  | X | X | X
| Affiliate Sell registration |  | MP090 | 미완료 |  |  |  | X | X | X